## Summary
Summary: hours, rate, price and key dates
Yellow cells with blue text are inputs. Everything else is calculated.
Item | Value | Notes
Hourly rate (USD) | 45 | Input. Change it and the price below updates.
Estimated hours (all build steps) | 72 | Sum of the Hours column on the Timeline sheet.
Fixed price (USD) | 3240 | Hours x rate. Fixes during the Oct 16 to Nov 1 acceptance window are included.
Contract start | 2026-10-05
Working build | 2026-10-15
Hard deadline | 2026-11-01
Working days in the build | 9
Average hours per working day | 8
Calendar days of buffer before the deadline | 17 | Covers Web Store review turnaround and acceptance fixes.
Hours by phase
Phase | Hours | Share of total
Release engineering | 20 | 27.78%
CI and trust | 8 | 11.11%
Extension | 8 | 11.11%
Safety layer | 19 | 26.39%
Testing | 11 | 15.28%
Docs | 3 | 4.167%
Communication | 3 | 4.167%
Check: phases add up to the total | OK
Prepared by James for the Manifest V3 form-fill extension post. Source of every number: this workbook (estimates by James).

## Timeline
Chrome extension (MV3) build: detailed timeline
All 16 build steps finish by Thursday Oct 15, 2026. Oct 16 to Nov 1 is acceptance buffer, included in the fixed price.
Step | Phase | Functionality | What gets built | Done when (acceptance check) | Start | End | Hours | Depends on | Deliverable | Needs from you
S01 | Release engineering | Deterministic build and pinned toolchain | Zero-dependency build script; Node pinned (.nvmrc, engines); LF and BOM normalization; file-type allowlist; stored zip with fixed timestamps and order | Two builds on different machines produce identical SHA256SUMS and an identical zip | 2026-10-05 | 2026-10-05 | 4 |  | scripts/build.mjs, release/SHA256SUMS | Add me to the GitHub repo, or I create it and transfer ownership to you
S02 | Release engineering | Hash list and reproducibility check in CI | sha256sum-compatible hash list; PR workflow builds twice in separate folders and compares; hash list uploaded as an artifact | A PR fails if the two builds differ by a single byte | 2026-10-05 | 2026-10-05 | 4 | S01 | .github/workflows/pr.yml
S03 | CI and trust | Three trust tiers with short-lived tokens | PR jobs get no id-token at all; staging and release environments; required reviewer on release; OIDC sub claim customized to repo + environment + workflow file; actions pinned to commit SHAs | A PR job cannot obtain any cloud token; a staging token cannot assume the release role | 2026-10-06 | 2026-10-06 | 4 | S02 | Workflow permissions, environment settings, sub-claim config | Approve the environment and reviewer settings I send (10 minutes)
S04 | Release engineering | Signed-tag release gate | Annotated SSH-signed tag whose message is the hash list; allowed signers read from the protected release environment; tag must equal manifest version; clean rebuild compared file for file | Unsigned tag, unknown key, late code change or wrong version each stop the release (automated tests) | 2026-10-06 | 2026-10-06 | 4 | S01, S03 | scripts/verify-tag.mjs, release.yml gate job | Send the public SSH key(s) of whoever signs releases
S05 | Extension | MV3 shell with minimum permissions | Manifest with activeTab and scripting only; one host permission (your backend); CSP connect-src locked to the backend; module service worker; popup; on-demand injection, no static content scripts | chrome.storage does not exist at runtime; a fetch to any other origin is blocked by CSP (browser test) | 2026-10-07 | 2026-10-07 | 4 | S01 | extension/manifest.json, background.js, popup
S06 | Extension | Ticket handoff and backend fetch | Web app sends a short-lived ticket via externally_connectable; sender origin checked; ticket kept in memory only; active tab must match the ticket's portal; fetch with no-store, no credentials, no redirects; response shape validated | Wrong site, expired ticket and messages from other sites are refused, and nothing is filled | 2026-10-07 | 2026-10-07 | 4 | S05 | Ticket flow + integration contract note | Ticket and fill-values API contract (from the AWS engineer)
S07 | Safety layer | Field discovery on third-party pages | Signals from labels, aria-labelledby, aria-label, placeholder, title, name/id, autocomplete; open shadow roots; visibility; fillable field kinds; embedded frames counted and reported | Every field in the sample portals, including shadow DOM, is discovered with the right signals | 2026-10-08 | 2026-10-08 | 4 | S05 | collect() in fill-engine.js | List of target portals, plus test pages or test accounts
S08 | Safety layer | Exact-one-match-or-skip matcher | Candidate set per value; two-way uniqueness (one value, one field); explicit skip reasons; matching rules frozen and shipped inside the signed extension | Ambiguous, shared-field and no-match cases fill nothing (unit tests) | 2026-10-08 | 2026-10-08 | 4 | S07 | plan() in fill-engine.js, field-rules.js
S09 | Safety layer | Value safety checks | maxlength, pattern, input type, single matching select option, date format only when the field states it, never overwrite, read-only and disabled, passwords and files excluded, backend value format | Each rule has a passing unit test that proves the skip | 2026-10-09 | 2026-10-09 | 4 | S08 | valueFor() and rules
S10 | Safety layer | Fill writer and review highlights | Native value setters plus input and change events (works with React and Angular forms); read-back; filled fields outlined solid, ambiguous ones dashed; clear highlights; never submits or clicks | Values survive the page re-rendering; the submit counter stays at zero (browser test) | 2026-10-09 | 2026-10-09 | 3 | S08 | write(), mark(), clearMarks()
CP1 | Communication | Weekly checkpoint 1 (written) | What's done, what's next, decisions needed, explicit actions for you | Sent Friday Oct 9 | 2026-10-09 | 2026-10-09 | 1 |  | Written update | Read and answer any decisions listed
S11 | Safety layer | Zero-storage and zero-logging enforcement | Policy gate in CI (storage, logging, submission, dynamic code, network egress, permissions, CSP); worker strips reports to statuses and reasons; errors as codes, never messages with data | The gate fails on each injected violation (tests) and passes on the release build | 2026-10-12 | 2026-10-12 | 4 | S05 | scripts/check-policy.mjs
S12 | Testing | Unit test suite | Matcher fixtures from real portal patterns; hash list; build determinism incl. Windows line endings; zip and CRX parsing; policy gate | All green in CI on every PR | 2026-10-12 | 2026-10-12 | 4 | S08, S09, S11 | test/*.test.mjs
S13 | Testing | Real-browser tests | Playwright on real Chromium with the exact release files; extension loaded unpacked; full ticket to fill chain against a local HTTPS mirror of the backend origin | All green in CI; values never appear in the popup report | 2026-10-13 | 2026-10-13 | 4 | S10, S12 | e2e/*.spec.mjs
S14 | CI and trust | Staging pipeline and Web Store upload | GitHub OIDC to Google Workload Identity Federation to a service account; Chrome Web Store API v2 upload to the staging item; first submission early to start the review clock | Staging upload runs from CI with no stored secret | 2026-10-13 | 2026-10-13 | 4 | S03 | staging.yml, setup commands | Chrome Web Store developer account and item; Google Cloud project (I send the exact commands)
S15 | Release engineering | Published-package verifier | Downloads the CRX the store serves; parses CRX3; hashes every file; compares with the signed list; store additions handled by an explicit, printed allowlist | Passes on the store's package; fails on any other difference (tests) | 2026-10-14 | 2026-10-14 | 5 | S04, S14 | scripts/verify-webstore.mjs, scheduled job
S16 | Docs | Install procedure and runbooks | Install: Web Store listing, managed install by policy, unpacked for testing; release runbook; your-side checklist | Someone other than me can cut a release from the runbook | 2026-10-14 | 2026-10-14 | 3 | S15 | docs/INSTALL.md, docs/RELEASE.md
R1 | Release engineering | End-to-end release dry run | Sign tag, run the gate, upload to staging, verify the package | One full release completes from a signed tag with no manual edits | 2026-10-15 | 2026-10-15 | 3 | S04, S14, S15 | Dry-run log
R2 | Testing | Acceptance run against your written criteria | Walk all 16 steps' acceptance criteria and fix anything that falls short | Every criterion marked pass with evidence | 2026-10-15 | 2026-10-15 | 3 | All | Acceptance checklist with evidence | Review the checklist
CP2 | Communication | Working build handover and checkpoint 2 | Recorded walkthrough, written update, what remains for Nov 1 | Working build delivered Thursday Oct 15 | 2026-10-15 | 2026-10-15 | 2 | R1, R2 | Walkthrough video + written update | Acceptance review (Oct 16 to Nov 1)
B1 | Buffer | Acceptance window until the hard deadline | Your review, Web Store review turnaround, fixes from acceptance. Included in the fixed price. | Published, verified build by Nov 1 | 2026-10-16 | 2026-11-01 | 0 | CP2 | Final release
[6 empty] | Total hours | 72
Blue numbers are estimates you can edit; every total in this workbook recalculates from them. "incl." = included in the fixed price, no extra hours billed.

## Gantt
Gantt: Oct 5 to Nov 1, 2026
Bars are drawn by formula from the Start and End dates on the Timeline sheet. Grey columns are weekends. | [15 empty] | Working build | [16 empty] | Hard deadline
[6 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
Step | Phase | Functionality | Start | End | Hours | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
S01 | Release engineering | Deterministic build and pinned toolchain | 2026-10-05 | 2026-10-05 | 4
S02 | Release engineering | Hash list and reproducibility check in CI | 2026-10-05 | 2026-10-05 | 4
S03 | CI and trust | Three trust tiers with short-lived tokens | 2026-10-06 | 2026-10-06 | 4
S04 | Release engineering | Signed-tag release gate | 2026-10-06 | 2026-10-06 | 4
S05 | Extension | MV3 shell with minimum permissions | 2026-10-07 | 2026-10-07 | 4
S06 | Extension | Ticket handoff and backend fetch | 2026-10-07 | 2026-10-07 | 4
S07 | Safety layer | Field discovery on third-party pages | 2026-10-08 | 2026-10-08 | 4
S08 | Safety layer | Exact-one-match-or-skip matcher | 2026-10-08 | 2026-10-08 | 4
S09 | Safety layer | Value safety checks | 2026-10-09 | 2026-10-09 | 4
S10 | Safety layer | Fill writer and review highlights | 2026-10-09 | 2026-10-09 | 3
CP1 | Communication | Weekly checkpoint 1 (written) | 2026-10-09 | 2026-10-09 | 1
S11 | Safety layer | Zero-storage and zero-logging enforcement | 2026-10-12 | 2026-10-12 | 4
S12 | Testing | Unit test suite | 2026-10-12 | 2026-10-12 | 4
S13 | Testing | Real-browser tests | 2026-10-13 | 2026-10-13 | 4
S14 | CI and trust | Staging pipeline and Web Store upload | 2026-10-13 | 2026-10-13 | 4
S15 | Release engineering | Published-package verifier | 2026-10-14 | 2026-10-14 | 5
S16 | Docs | Install procedure and runbooks | 2026-10-14 | 2026-10-14 | 3
R1 | Release engineering | End-to-end release dry run | 2026-10-15 | 2026-10-15 | 3
R2 | Testing | Acceptance run against your written criteria | 2026-10-15 | 2026-10-15 | 3
CP2 | Communication | Working build handover and checkpoint 2 | 2026-10-15 | 2026-10-15 | 2
B1 | Buffer | Acceptance window until the hard deadline | 2026-10-16 | 2026-11-01 | 0
Legend
Release engineering
CI and trust
Extension
Safety layer
Testing
Docs
Communication
Buffer
Note on G4: First day of the chart (input). Every other date is this +1.

## Your actions
What I need from you, and when
Everything on your side, in date order. Mark Done with an x as you go (yellow cells).
Needed by | Action | Why it matters | Time for you | Done
2026-10-05 | Add me to the GitHub repository (or approve my transfer of a new one) | CI, environments and branch rules live there | 5 min
2026-10-06 | Approve the staging and release environment settings I send, and name the release reviewer | Release jobs wait for this reviewer | 10 min
2026-10-06 | Send the public SSH key of each person allowed to sign releases | The release gate only trusts these keys | 5 min
2026-10-07 | Share the ticket and fill-values API contract (from the AWS engineer) | The extension's only network call depends on it | Forward a doc
2026-10-08 | List the target portals, with test pages or test accounts if they exist | Matching rules are tuned against real forms | 20 min
2026-10-09 | Read checkpoint 1 and answer any decisions in it | Keeps week two unblocked | 10 min
2026-10-12 | Create or confirm the Chrome Web Store developer account and staging item | Needed before the first upload (one-time US$5 fee) | 15 min
2026-10-12 | Create a Google Cloud project, or let me run the setup commands I send | Workload Identity Federation for keyless publishing | 15 min
2026-10-15 | Review the working build and the acceptance checklist | Starts the acceptance window | 1 to 2 hours
Example: type x in Done once an action is complete.
Actions done | 0 of 9

## Assumptions
Assumptions that would change the number
If any of these turns out different, this is what it does to the estimate.
Assumption | If it turns out different | Impact on estimate
The 16 written steps match this breakdown in scope | Re-estimate within a day of reading them | up to +16 h
The ticket and fill-values API exists or is stubbed by Oct 7 | I write the contract and a stub with the AWS engineer | +6 to 8 h
Up to about 10 target portals with ordinary HTML forms | Each heavily scripted or multi-step portal needs its own fixtures and rules | +2 to 4 h per portal
Fields are in the top page or open shadow roots, not cross-origin frames | Frame support means per-frame injection and matching | +8 h
Matching rules ship inside the extension (signed with each release) | If rules come from the backend per portal, they need their own signing and review path | +10 h
Chrome only (Edge works from the same package) | Firefox needs a second manifest and build target | +12 h
'Stores nothing' allows the in-memory ticket in the service worker | If even that is out, the web app must hand over the ticket at fill time | +4 h